## Sheet2
Project | Type | Cost_Name | QTY_UOM | QTY | Unit_Cost | Estimated_Cost | Actual_Cost | Normalized_Cost | Tower Gross Floor Area (GFA) | Parking Gross Floor Area (GFA) | Retail/Commercial GFA | Total Units | Average sf/unit | Studio | 1B | 2B | 3B | Penthouse | Total Parking | Average sf/stall | Total Duration (mos) | Project Start Year | Project Finish Year | Cost Normalization Rate
A | [8 empty] | 600000 | 400000 | 10000 | 400 | 1500 | 40 | 250 | 100 | 10 | 0 | 1142.8571 | 350 | 30 | 2012 | 2014 | 4
B | [8 empty] | 150000 | 60000 | 50000 |  | 310 | 483.871 | 75 | 50 | 25 |  | 160 | 375 | 24 | 2015 | 2017 | 4
A | Tower | General Requirements |  |  |  | 15000000 | 15300000 | 15000000
A | Tower | Demo |  |  |  | 1000000 | 980000 | 1000000
A | Tower | Concrete | sf | 60000 | 75 | 45000000 | 45900000 | 45000000
A | Tower | Reinforcing Steel |  |  |  | 12000000 | 11760000 | 12000000
A | Tower | CMU |  |  |  | 1200000 | 1224000 | 1200000
A | Tower | Structural Steel |  |  |  | 3000000 | 2940000 | 3000000
A | Tower | Carpentry |  |  |  | 4200000 | 4284000 | 4200000
A | Tower | Casework |  |  |  | 3000000 | 2940000 | 3000000
A | Tower | Waterproofing |  |  |  | 1200000 | 1224000 | 1200000
A | Tower | Roofing |  |  |  | 1200000 | 1176000 | 1200000
A | Tower | Doors |  |  |  | 3000000 | 3060000 | 3000000
A | Tower | Windows |  |  |  | 9000000 | 8820000 | 9000000
A | Tower | Gypsum Board |  |  |  | 7200000 | 7344000 | 7200000
A | Tower | Painting |  |  |  | 3600000 | 3528000 | 3600000
A | Tower | Tile/Stone |  |  |  | 3000000 | 3060000 | 3000000
A | Tower | Flooring |  |  |  | 2400000 | 2352000 | 2400000
A | Tower | Specialties |  |  |  | 600000 | 612000 | 600000
A | Tower | Furnishing |  |  |  | 300000 | 294000 | 300000
A | Tower | Equipment |  |  |  | 600000 | 612000 | 600000
A | Tower | Appliances |  |  |  | 3000000 | 2940000 | 3000000
A | Tower | Elevators |  |  |  | 4200000 | 4284000 | 4200000
A | Tower | Fire Sprinkler |  |  |  | 3600000 | 3528000 | 3600000
A | Tower | Plumbing |  |  |  | 15000000 | 15300000 | 15000000
A | Tower | HVAC |  |  |  | 18000000 | 17640000 | 18000000
A | Tower | Electrical |  |  |  | 24000000 | 24480000 | 24000000
A | Tower | Hardscaping |  |  |  | 300000 | 294000 | 300000
A | Tower | Sitework |  |  |  | 3000000 | 3060000 | 3000000
A | Tower | Utilities |  |  |  | 600000 | 588000 | 600000
A | Tower | Landscaping |  |  |  | 600000 | 612000 | 600000
A | Tower | Irrigation |  |  |  | 450000 | 441000 | 450000
A | Tower | Fee |  |  |  | 10900000 | 11118000 | 10900000
A | Tower | Insurance |  |  |  | 2000000 | 1960000 | 2000000
A | Tower | Bond |  |  |  | 7600000 | 7752000 | 7600000
A | Tower | Tax |  |  |  | 5500000 | 5390000 | 5500000
A | Parking | General Requirements |  |  |  | 2000000 | 2040000 | 3078908.1126
A | Parking | Demo |  |  |  |  | 0 | 0
A | Parking | Concrete | sf | 40000 | 75 | 30000000 | 30600000 | 46183621.6895
A | Parking | Reinforcing Steel |  |  |  | 8000000 | 7840000 | 12315632.4505
A | Parking | CMU |  |  |  | 800000 | 816000 | 1231563.2451
A | Parking | Structural Steel |  |  |  | 400000 | 392000 | 615781.6225
A | Parking | Carpentry |  |  |  | 150000 | 153000 | 230918.1084
A | Parking | Casework |  |  |  | 0 | 0 | 0
A | Parking | Waterproofing |  |  |  | 300000 | 306000 | 461836.2169
A | Parking | Roofing |  |  |  | 200000 | 196000 | 307890.8113
A | Parking | Doors |  |  |  | 100000 | 102000 | 153945.4056
A | Parking | Windows |  |  |  | 200000 | 196000 | 307890.8113
A | Parking | Gypsum Board |  |  |  | 400000 | 408000 | 615781.6225
A | Parking | Painting |  |  |  | 300000 | 294000 | 461836.2169
A | Parking | Tile/Stone |  |  |  | 0 | 0 | 0
A | Parking | Flooring |  |  |  | 0 | 0 | 0
A | Parking | Specialties |  |  |  | 100000 | 102000 | 153945.4056
A | Parking | Furnishing |  |  |  | 100000 | 98000 | 153945.4056
A | Parking | Equipment |  |  |  | 125000 | 127500 | 192431.757
A | Parking | Appliances |  |  |  | 0 | 0 | 0
A | Parking | Elevators |  |  |  | 400000 | 408000 | 615781.6225
A | Parking | Fire Sprinkler |  |  |  | 2400000 | 2352000 | 3694689.7352
A | Parking | Plumbing |  |  |  | 1000000 | 1020000 | 1539454.0563
A | Parking | HVAC |  |  |  | 200000 | 196000 | 307890.8113
A | Parking | Electrical |  |  |  | 2000000 | 2040000 | 3078908.1126
A | Parking | Hardscaping |  |  |  | 150000 | 147000 | 230918.1084
A | Parking | Sitework |  |  |  | 1200000 | 1224000 | 1847344.8676
A | Parking | Utilities |  |  |  | 300000 | 294000 | 461836.2169
A | Parking | Landscaping |  |  |  | 150000 | 153000 | 230918.1084
A | Parking | Irrigation |  |  |  | 75000 | 73500 | 115459.0542
A | Parking | Fee |  |  |  | 2900000 | 2958000 | 4464416.7633
A | Parking | Insurance |  |  |  | 522000 | 511560 | 803595.0174
A | Parking | Bond |  |  |  | 2100000 | 2142000 | 3232853.5183
A | Parking | Tax |  |  |  | 1500000 | 1470000 | 2309181.0845
B | Tower | General Requirements |  |  |  | 8400000 | 8232000 | 8400000
B | Tower | Demo |  |  |  | 250000 | 255000 | 250000
B | Tower | Concrete | sf | 150000 | 75 | 11250000 | 11025000 | 11250000
B | Tower | Reinforcing Steel |  |  |  | 3750000 | 3825000 | 3750000
B | Tower | CMU |  |  |  | 300000 | 294000 | 300000
B | Tower | Structural Steel |  |  |  | 750000 | 765000 | 750000
B | Tower | Carpentry |  |  |  | 1050000 | 1029000 | 1050000
B | Tower | Casework |  |  |  | 750000 | 765000 | 750000
B | Tower | Waterproofing |  |  |  | 300000 | 294000 | 300000
B | Tower | Roofing |  |  |  | 300000 | 306000 | 300000
B | Tower | Doors |  |  |  | 750000 | 735000 | 750000
B | Tower | Windows |  |  |  | 2250000 | 2295000 | 2250000
B | Tower | Gypsum Board |  |  |  | 1800000 | 1764000 | 1800000
B | Tower | Painting |  |  |  | 900000 | 918000 | 900000
B | Tower | Tile/Stone |  |  |  | 750000 | 735000 | 750000
B | Tower | Flooring |  |  |  | 600000 | 612000 | 600000
B | Tower | Specialties |  |  |  | 150000 | 147000 | 150000
B | Tower | Furnishing |  |  |  | 75000 | 76500 | 75000
B | Tower | Equipment |  |  |  | 150000 | 147000 | 150000
B | Tower | Appliances |  |  |  | 750000 | 765000 | 750000
B | Tower | Elevators |  |  |  | 1050000 | 1029000 | 1050000
B | Tower | Fire Sprinkler |  |  |  | 900000 | 918000 | 900000
B | Tower | Plumbing |  |  |  | 3750000 | 3675000 | 3750000
B | Tower | HVAC |  |  |  | 4500000 | 4590000 | 4500000
B | Tower | Electrical |  |  |  | 6750000 | 6615000 | 6750000
B | Tower | Hardscaping |  |  |  | 75000 | 76500 | 75000
B | Tower | Sitework |  |  |  | 750000 | 735000 | 750000
B | Tower | Utilities |  |  |  | 150000 | 153000 | 150000
B | Tower | Landscaping |  |  |  | 150000 | 147000 | 150000
B | Tower | Irrigation |  |  |  | 112500 | 114750 | 112500
B | Tower | Fee |  |  |  | 3100000 | 3038000 | 3100000
B | Tower | Insurance |  |  |  | 550000 | 561000 | 550000
B | Tower | Bond |  |  |  | 2200000 | 2156000 | 2200000
B | Tower | Tax |  |  |  | 1600000 | 1632000 | 1600000
B | Parking | General Requirements |  |  |  | 1500000 | 1470000 | 1500000
B | Parking | Demo |  |  |  |  | 0 | 0
B | Parking | Concrete | sf | 60000 | 74 | 4500000 | 4410000 | 4500000
B | Parking | Reinforcing Steel |  |  |  | 1500000 | 1530000 | 1500000
B | Parking | CMU |  |  |  | 120000 | 117600 | 120000
B | Parking | Structural Steel |  |  |  | 60000 | 61200 | 60000
B | Parking | Carpentry |  |  |  | 15000 | 14700 | 15000
B | Parking | Casework |  |  |  | 0 | 0 | 0
B | Parking | Waterproofing |  |  |  | 45000 | 44100 | 45000
B | Parking | Roofing |  |  |  | 30000 | 30600 | 30000
B | Parking | Doors |  |  |  | 15000 | 14700 | 15000
B | Parking | Windows |  |  |  | 30000 | 30600 | 30000
B | Parking | Gypsum Board |  |  |  | 6000 | 5880 | 6000
B | Parking | Painting |  |  |  | 45000 | 45900 | 45000
B | Parking | Tile/Stone |  |  |  | 0 | 0 | 0
B | Parking | Flooring |  |  |  | 0 | 0 | 0
B | Parking | Specialties |  |  |  | 15000 | 14700 | 15000
B | Parking | Furnishing |  |  |  | 50000 | 51000 | 50000
B | Parking | Equipment |  |  |  | 75000 | 73500 | 75000
B | Parking | Appliances |  |  |  | 0 | 0 | 0
B | Parking | Elevators |  |  |  | 60000 | 58800 | 60000
B | Parking | Fire Sprinkler |  |  |  | 360000 | 367200 | 360000
B | Parking | Plumbing |  |  |  | 150000 | 147000 | 150000
B | Parking | HVAC |  |  |  | 30000 | 30600 | 30000
B | Parking | Electrical |  |  |  | 300000 | 294000 | 300000
B | Parking | Hardscaping |  |  |  | 50000 | 51000 | 50000
B | Parking | Sitework |  |  |  | 120000 | 117600 | 120000
B | Parking | Utilities |  |  |  | 75000 | 76500 | 75000
B | Parking | Landscaping |  |  |  | 37500 | 36750 | 37500
B | Parking | Irrigation |  |  |  | 18750 | 19125 | 18750
B | Parking | Fee |  |  |  | 525000 | 514500 | 525000
B | Parking | Insurance |  |  |  | 95000 | 96900 | 95000
B | Parking | Bond |  |  |  | 267000 | 261660 | 267000
B | Parking | Tax |  |  |  | 260000 | 265200 | 260000
A | Project | General Requirements |  |  |  | 2550000 | 2601000 | 26170718.9574
A | Project | Demo |  |  |  | 1150000 | 1127000 | 1539454.0563
A | Project | Concrete |  |  |  | 312500 | 318750 | 115459054.2236
A | Project | Reinforcing Steel |  |  |  | 5100000 | 4998000 | 30789081.1263
A | Project | CMU |  |  |  | 700000 | 714000 | 3078908.1126
A | Project | Structural Steel |  |  |  | 3400000 | 3332000 | 5234143.7915
A | Project | Carpentry |  |  |  | 1900000 | 1938000 | 6696625.145
A | Project | Casework |  |  |  | 1650000 | 1617000 | 4618362.1689
A | Project | Waterproofing |  |  |  | 75000 | 76500 | 2309181.0845
A | Project | Roofing |  |  |  | 7400000 | 7252000 | 2155235.6788
A | Project | Doors |  |  |  | 2022000 | 2062440 | 4772307.5746
A | Project | Windows |  |  |  | 2220000 | 2175600 | 14162977.3181
A | Project | Gypsum Board |  |  |  | 1560000 | 1591200 | 11699850.828
A | Project | Painting |  |  |  | 8415000 | 8246700 | 6003870.8196
A | Project | Tile/Stone |  |  |  | 250000 | 255000 | 4618362.1689
A | Project | Flooring |  |  |  | 11295000 | 11069100 | 3694689.7352
A | Project | Specialties |  |  |  | 3780000 | 3855600 | 1077617.8394
A | Project | Furnishing |  |  |  | 315000 | 308700 | 615781.6225
A | Project | Equipment |  |  |  | 780000 | 795600 | 1116104.1908
A | Project | Appliances |  |  |  | 1056000 | 1034880 | 4618362.1689
A | Project | Elevators |  |  |  | 795000 | 810900 | 7081488.659
A | Project | Fire Sprinkler |  |  |  | 300000 | 294000 | 9236724.3379
A | Project | Plumbing |  |  |  | 300000 | 306000 | 24631264.901
A | Project | HVAC |  |  |  | 765000 | 749700 | 28018063.8249
A | Project | Electrical |  |  |  | 2300000 | 2346000 | 40025805.4642
A | Project | Hardscaping |  |  |  | 1875000 | 1837500 | 692754.3253
A | Project | Sitework |  |  |  | 900000 | 918000 | 6465707.0365
A | Project | Utilities |  |  |  | 810000 | 793800 | 1385508.6507
A | Project | Landscaping |  |  |  | 960000 | 979200 | 1154590.5422
A | Project | Irrigation |  |  |  | 300000 | 294000 | 808213.3796
A | Project | Fee |  |  |  | 105000 | 107100 | 21244465.9771
A | Project | Insurance |  |  |  | 450000 | 441000 | 3882503.13
A | Project | Bond |  |  |  | 800000 | 816000 | 14932704.3463
A | Project | Tax |  |  |  | 1170000 | 1146600 | 10776178.3942
B | Project | General Requirements |  |  |  | 975000 | 955500 | 975000
B | Project | Demo |  |  |  | 3787500 | 3863250 | 3787500
B | Project | Concrete |  |  |  | 4518750 | 4428375 | 4518750
B | Project | Reinforcing Steel |  |  |  | 7275000 | 7420500 | 7275000
B | Project | CMU |  |  |  | 170000 | 166600 | 170000
B | Project | Structural Steel |  |  |  | 1017000 | 1037340 | 1017000
B | Project | Carpentry |  |  |  | 410000 | 401800 | 410000
B | Project | Casework |  |  |  | 2700000 | 2754000 | 2700000
B | Project | Waterproofing |  |  |  | 1262500 | 1237250 | 1262500
B | Project | Roofing |  |  |  | 3412500 | 3480750 | 3412500
B | Project | Doors |  |  |  | 5650000 | 5537000 | 5650000
B | Project | Windows |  |  |  | 2900000 | 2958000 | 2900000
B | Project | Gypsum Board |  |  |  | 5000000 | 4900000 | 5000000
B | Project | Painting |  |  |  | 3400000 | 3468000 | 3400000
B | Project | Tile/Stone |  |  |  | 1650000 | 1617000 | 1650000
B | Project | Flooring |  |  |  | 4575000 | 4666500 | 4575000
B | Project | Specialties |  |  |  | 8900000 | 8722000 | 8900000
B | Project | Furnishing |  |  |  | 2142000 | 2184840 | 2142000
B | Project | Equipment |  |  |  | 2280000 | 2234400 | 2280000
B | Project | Appliances |  |  |  | 1575000 | 1606500 | 1575000
B | Project | Elevators |  |  |  | 8415000 | 8246700 | 8415000
B | Project | Fire Sprinkler |  |  |  | 295000 | 300900 | 295000
B | Project | Plumbing |  |  |  | 11325000 | 11098500 | 11325000
B | Project | HVAC |  |  |  | 3795000 | 3870900 | 3795000
B | Project | Electrical |  |  |  | 345000 | 338100 | 345000
B | Project | Hardscaping |  |  |  | 786000 | 801720 | 786000
B | Project | Sitework |  |  |  | 1101000 | 1078980 | 1101000
B | Project | Utilities |  |  |  | 795000 | 810900 | 795000
B | Project | Landscaping |  |  |  | 300000 | 294000 | 300000
B | Project | Irrigation |  |  |  | 315000 | 321300 | 315000
B | Project | Fee |  |  |  | 815000 | 798700 | 815000
B | Project | Insurance |  |  |  | 2375000 | 2422500 | 2375000
B | Project | Bond |  |  |  | 1875000 | 1837500 | 1875000
B | Project | Tax |  |  |  | 960000 | 979200 | 960000